## Week 1
Week | Task name | Assignee | Status | Note
1 | Wireframe control panel User + layout | Samiha | Done | Done On time
1 | Wireframe control panel psychologist +sql | Saly | Done | Done On time
1 | Wireframe Home page + Session page | Mais | Done | Done On time
1 | Frontend login and sign in | Basil | Done | Done On time
1 | Frontend Footer | Dina | Done | Done On time
1 | Frontend Header | malak | Done | Done On time
1 | Wireframe control panel User +psychologist | Malak abu amra | Not Done | Not Done (samiha and saly do this task )

## Week 2
Week | Task name | Assignee | Status | Note
2 | Backend Models | Samiha
2 | Frontend control panel psychologist | Saly
2 | Frontend Home Page | Mais
2 | Frontend control panel Admin | Basil
2 | Frontend Session page | Dina
2 | Frontend control panel User | malak
2 |  | Malak abu amra |  | Absent